## Slide 1: Eurodiplomats March 2021
Panayiotis Angelides

## Slide 2: PROJECT DURATION
24 months
Start date: 01.03.2021

## Slide 3: PAYMENT ARRANGEMENTS
*Special payment arrangements are foreseen for organisations with "not satisfactory" financial capacity
Payments | % | When
Pre-financing | 30 | Within 30 days after the signature of the Grant Agreement
Further pre-financing | 30 | Within 60 days after the submission and upon approval of the Interim Report
Final Payment | 40 | Within 60 days after the submission and upon approval of the Final Report

## Slide 4: PAYMENT ARRANGEMENTS
FURTHER PREFINANCING
Following the interim report with proof that the 70% of the first pre-financing has been spent
BALANCE PAYMENT
Evaluation of the Final Report (FR) - Last installment
Amount to be determined based on: the eligible costs incurred after the evaluation/approval of the FR and its supporting documents
Possible grant reduction for poor/partial/late implementation of the Project, the products and outputs produced.

## Slide 5: BUDGET HEADINGS
PROJECT MANAGEMENT& IMPLEMENTATION (PMI)
TRANSNATIONAL PROJECT MEETINGS (TPMs)
INTELLECTUAL OUTPUTS (IOs)
MULTIPLIER EVENTS (MEs)
LEARNING/TEACHING/TRAINING ACTIVITIES (LTTs)
SPECIAL NEEDS (SN)
EXCEPTIONAL COSTS (EC)

## Slide 6: 1. PROJECT MANAGEMENT & IMPLEMENTATION
What can be covered?
Planning, finances, coordination and communication between partners, Small scale learning/teaching/training materials, tools etc.
Information, promotion, dissemination (flyers, leaflets, websites etc.) Participants travel insurance
Costs for additional participants in mobilities. Possible hosting expenses.
Proof?
Implementation of the project activities
Final Report
Platform of Project Results/available for checks and audits

## Slide 7: 2. TRASNATIONAL PROJECT MEETINGS (1/2)
For planning, coordination, evaluation, preparation, dissemination
Hosted by one of the participating organisations
Participants in TPM need to have a formal link with beneficiary organizations (staff of the partnership organizations)
Package for travel and subsistence costs, regardless of the duration of the meeting (online distance band calculator). Reporting in the Mobility Tool by the coordinator (name of participant, place of origin & venue, distance band)

## Slide 8: 2. TRASNATIONAL PROJECT MEETINGS (2/2)
SUPPORTING DOCUMENTS
1. Certificate of participation issued and signed by the receiving institution specifying:
the name of the participant
the purpose of the activity
starting and end date
2. Agenda of the TPM
3. Participants list signed by receiving institution & participants specifying:
title, date, place of the TPM
participants name, email, address, signature
name and address of sending organisation

## Slide 9: 3. INTELLECTUAL OUTPUTS (1/2)
Only IOs that have been approved
Number of days of work per person on the basis of timesheets (days x unit per day – according to staff category & country)
Only staff members of beneficiaries can be declared
NO SUBCONTRACTING for the production of IOs
Staff categories “manager” & “administrative staff”: only if applied for and adequately justified and approved by the CY NA
Only paid personnel can claim staff costs for IOs

## Slide 10: 3. INTELLECTUAL OUTPUTS (2/2)
SUPPORTING DOCUMENTS
1. Proof that the IO has been realized and it is of acceptable quality:
uploaded in the E+Project Results Platform (material available for checks)
2. Time sheets per person:
signed by employees and employers/legal representative
name, category of staff, dates, total number of days, reference to IO
3. Proof of the nature of the relationship between the person and the beneficiary concerned

## Slide 11: 4. MULTIPLIER EVENTS (1/2)
Only ME associated with approved IOs
If an approved IO is not developed its respective ME is not eligible
Only participants from organisations other than the beneficiaries can be counted up for the number of persons (locals and internationals)

## Slide 12: 4. MULTIPLIER EVENTS (2/2)
SUPPORTING DOCUMENTS
1. Agenda of the ME
2. Participants list signed by hosting institution:
title, date, place of the ME
participants name, email, address, signature
name and address of their organisation

## Slide 13: 5. LEARNING TEACHING TRAINING ACTIVITIES (1/3)
WHO CAN PARTICIPATE
Persons who have a direct link with beneficiary organizations (coordinator & partners):
  Staff of beneficiary organizations (Professors, teachers, trainers and educational administrative staff employed at a participating organisation)
  Learners: Students of HEI, Apprentices, VET students, adult learners, pupils of any age accompanied by school staff (pupils participating in short term exchanges)

## Slide 14: 5. LEARNING TEACHING TRAINING ACTIVITIES (2/3)
Travel and Subsistence costs are separate
The eligible minimum duration of mobility activities is the minimum duration of the activity excluding travel
1 or 2 travel days may be eligible for funding within individual if requested (1 day before the beginning of the activity and 1 following the last day of the activity)
Travel Support to participants within the same country is eligible if the distance between the place of departure and place of arrival is at least 10km (online distance calculator) and more than 2 different Programme countries participate in the LTT
The activities take place at the place of the hosting organization
* Place of departure: the place of the sending organisation Place of arrival: place of the hosting organisation

## Slide 15: 5. LEARNING TEACHING TRAINING ACTIVITIES (3/3)
SUPPORTING DOCUMENTS
Certificate of participation issued and signed by the receiving institution specifying:
  the name of the participant
  the purpose of the activity
  starting and end date

## Slide 16: 6. SPECIAL NEEDS
For participation in LTTs &TPMs
Support on the basis of real costs for participants with special needs and accompanying persons
Includes all costs and all means of travel from the point of origin to the point of destination (including travel from/to the airport to/from the hotel)
100% of the eligible costs actually incurred
Reporting and receipts needed only for additional expenses

## Slide 17: 7. EXCEPTIONAL COSTS
Sub-contracting of goods and services that cannot be provided by beneficiaries themselves
Depreciation costs of equipment purchased (no office equipment)
In the case of equipment purchase/rental/ lease only the amount corresponding to the share of time of the use of the equipment of the project can be claimed
75% of the eligible costs actually incurred

## Slide 18: 7. EXCEPTIONAL COSTS
SUPPORTING DOCUMENTS
All supporting documents required at final report stage
Contractual agreement between the beneficiary and the organisation which is going to provide the service.
- where a procurement of goods/works/ services is required, the beneficiaries shall award the contract to the tender offering best value for money or, as appropriate, to the tender offering the lowest price, avoiding any conflict of interest
Invoice and receipt of payment for the services or purchases at final report stage

## Slide 19: BUDGET
The maximum Grant amount cannot be increased
The maxima set in the Programme Guide for each budget heading cannot be increased
All Budget Headings are based on " UNIT COSTS" except Special Needs and Exceptional Costs that are based on " REAL COSTS"
Changes within the same budget category are allowed ( increase the number of participants, mobilities etc), provided that there is no significant deviation from the initial project results/ aims
Budget transfers between different budget categories without an amendment
Budget transfers between different budget categories with an amendment

## Slide 20: BUDGET TRANSFERS WITHOUT AN AMENDMENT
Transfers up to 20% of the funds allocated from each budget heading to any other budget heading category except PMI and EC
Budget can be transferred to SN even if no funds have been allocated to that category initially. The maximum increase of 20% of this budget category does not apply. Transfer from SN to other categories is not allowed
The budget categories must exist already in the Grant Agreement
PMI and EC cannot be increased

## Slide 21: CHECKS AND AUDITS
Final Report check
Desk-check (at or after the final report stage)
On the spot check (at the premises of the beneficiaries)
  During the action
  After the action
All relevant documents to the project must be kept for at least 5 years after the completion of the agreement
All financial reports need to be consistent with the accounting records kept

## Slide 22
Thank you very much!
Comments?
For more info
  Panayiotis Angelides Angelides.p@unic.ac.cy