‘Εmpowering children to act as cultural

diplomats for a robust and resilient Europe’

Eurodiplomats

Project reference: 2020-1-CY01-KA227-SCH-082681

MINUTES of

Meeting in Madrid, Spain, January 14th, 2022

Meeting Venue:

Colegio BrotMadrid-Fundación Aprender.

Address: Calle de Blas Cabrera 88, Madrid

Metro Station Aluche.

Attendees:

P1: UNIC, Cyprus (Panayiotis Angelides & Christina Hadjisoteriou)

P2: Fundacion Aprender, Spain (Selina Martin-online)

P3: Asociación Instituto de Técnicas Educativas - I.T.E, Spain (Gonzalo Santamaria, Louis )

P4: Platon, Greece (Blatsios Spyridon)

P5: University of Macedonia, Greece (Ioannis Lefkos- online)

P6: 18th Primary School, Limassol Ayios Antonios (Nicos Papaevripides, Stalo Antoniou, Yiouli Pelekanou)

P7: VisMedNet, Malta (Antoine Gambin, )

P8: De la Salle College sixth form, Malta (John Portelli, Maria Cachia on-line)

Meeting Agenda

| Friday 14th January 2022 |  |  |
| --- | --- | --- |
| Time | Issue | Partner |
| 9:00 | Welcome and introduction | Fundacion Aprender UNIC |
| 9.05 | Presentation of the progress so far* * Each partner has to prepare a 5-minute presentation about the progress of O1 and O2 Actions ITE: UNIC is expecting the revised activities Platon: To send to UNIC all activities- Unic will send feedback Uof Macedonia: Send to Unic the revised activities 18th primary school: Done VisMedNet: Unic will send feedback De la Salle: Send to Unic the activities – UNic will send feedback UNIC: Done Aprender: Complete all activities by 15th of February 2022 VisMedNet Submit O1/A4 by 31/1/2022 Un of Macedonia: Comparative report Deadline 25/1/2022 Translation of Comparative report in Spanish, Greek and Maltese 28/2/2022 O1/A6 Translation in Greek 28/2/2022 | All partners |
| 10.00 | - Content of the project O2 - O2/A1 The EURODIPLOMATS Resources and Activities Toolkit - 1st version - O2/A2 Workshops - O2/A3 The EURODIPLOMATS Resources and Activities Toolkit - 2nd version - O2/A4 EURODIPLOMATS Teachers' Handbook - O2/A5 EURODIPLOMATS Children's Handbook Actions UNIC presented O2 and how the workshops O2/A2 should take place. All templates were explained. All templates will be send to partners O2/A2 All schools have to implement 6 activities and complete the implementation reports. Teacher reports (one from each teacher involved in the implementation) 6 student reports 1 comprehensive implementation report Deadline: 31/5/2022 | UNIC All partners |
| 11.00 | Coffee break | Fundacion Aprender |
| 11.30 | - Content of the project (continue) - O2/A1 The EURODIPLOMATS Resources and Activities Toolkit - 1st version - O2/A2 Workshops - O2/A3 The EURODIPLOMATS Resources and Activities Toolkit - 2nd version - O2/A4 EURODIPLOMATS Teachers' Handbook - O2/A5 EURODIPLOMATS Children's Handbook Actions O2/A4 EURODIPLOMATS Teachers' Handbook O2/A5 EURODIPLOMATS Children's Handbook ITE and VisMedNet: Deadline 1/5/2022 | UNIC All partners |
| 13.00 | Lunch | Fundacion Aprender |
| 14.00 | Dissemination - Website –UNIC Ask designer to add tabs Change the contact info of VisMedNet All partners to add the link of the project on their website Social Media VisMedNet: Facebook De la Salle: Linkedin 18th primary School: etwining U Macedonia: Slight share Multiplier events Cyprus-Conference Malta Greece Spain To be organised between Sep 2022 and Feb 2023 Videos Platon- to submit the first two videos 1 Teacher-teacher methodology (two minutes) 1 Children to children methodology Deadline: 28 Feb 2022 Videos about the implementation of the activities (3 videos) Deadline: 31/5/2022 | All partners |
| 15.00 | - Financial and administrative issues - Progress Report Send a template for timesheets 15th of March 2022 –deadline for submitting the timesheets All partners have to submit contracts with their organisation for all people involved in the project C1 Training event It will be organised in Katerini, Greece, 1-3/6/2022 Arrival day 31/5/2022-Departure day 4/6/2022 | UNIC |
| 16.00 | Internal Evaluation Meeting evaluation Final reflections | All partners |
| 17:00 | End of meeting |  |

In case of problems: Tel.  Selina Martin 0034 683235591