‘Εmpowering children to act as cultural

diplomats for a robust and resilient Europe’

Eurodiplomats

Project reference: 2020-1-CY01-KA227-SCH-082681

MINUTES of

Meeting On-line 12 July 2021

17.00 (16.00 CET)

Meeting Link:

Eurodiplomats Meeting

Hosted by Panayiotis Angelides

https://globaltraining.webex.com/globaltraining/j.php?MTID=m40698dac874ef430e5f2352d35285416

Monday, Jul 12, 2021 5:00 pm

Meeting number: 137 204 0199

Password: July2021

Expected Attendees:

P1: UNIC, Cyprus (Panayiotis Angelides & Christina Hadjisoteriou)

P2: Fundacion Aprender, Spain (IRENE RANZ, Selina Martin)

P3: Asociación Instituto de Técnicas Educativas - I.T.E, Spain (Gonzalo Santamaria)

P4: Platon, Greece (Blatsios Spyridon)

P5: University of Macedonia, Greece (Ioannis Lefkos)

P6: 18th Primary School, Limassol Ayios Antonios (Nicos Papaevripides, Yiouli)

P7: VisMedNet, Malta (Antoine Gambin)

P8: De la Salle College sixth form, Malta (John Portelli)

Meeting Agenda

| Time | Issue | Partner |
| --- | --- | --- |
| 17:00 | Welcome and introduction | UNIC |
| 17.05 | - Content of the project O1 - O1/A1 National Teachers' and Children’s Needs Analysis 16/7/2021 VisMedNet 19/7/2021 University of Macedonia - O1/A2 National Analyses of the State of Art in the National Languages - O1/A3 Group of Experts. - O1/A4 Elaboration of the national reports in English 31/7/2021 UNIC, ITE, VisMedNet, Un. Of Macedonia (see example) - O1/A5 Comparative Analysis 15/9/2021 University of Macedonia - O1/A6 The EURODIPLOMATS cultural diplomacy methodological tool 15/9/2021 All involved O2 - O2/A1 The EURODIPLOMATS Resources and Activities Toolkit - 1st version First activity 31/8/2021 The rest 30/11/2021 - O2/A2 Workshops - O2/A3 The EURODIPLOMATS Resources and Activities Toolkit - 2nd version - O2/A4 EURODIPLOMATS Teachers' Handbook - O2/A5 EURODIPLOMATS Children's Handbook | UNIC All partners |
| 18.20 | Financial and administrative issues Partner Agreement | UNIC |
| 18.40 | Dissemination - Website -UNIC - Next meeting Internal Evaluation Meeting evaluation | UNIC |
| 19:00 | End of meeting |  |