‘Εmpowering children to act as cultural

diplomats for a robust and resilient Europe’

Eurodiplomats

Project reference: 2020-1-CY01-KA227-SCH-082681

Minutes of

Meeting On-line 15 October 2021

17.00 (16.00 CET)

Meeting Link:

https://globaltraining.webex.com/globaltraining/j.php?MTID=m3d38337bcd9eecd1d54e46641e8e3f15

Meeting number: 2730 968 8308

Password: 2021

Eurodiplomats Meeting

Hosted by Panayiotis Angelides

Expected Attendees:

P1: UNIC, Cyprus (Panayiotis Angelides & Christina Hadjisoteriou)

P2: Fundacion Aprender, Spain (Marta Miranda, Pablo Mato and Eva del Olmo)

P3: Asociación Instituto de Técnicas Educativas - I.T.E, Spain (Gonzalo Santamaria, Selina Martin)

P4: Platon, Greece (Blatsios Spyridon)

P5: University of Macedonia, Greece (Ioannis Lefkos)

P6: 18th Primary School, Limassol Ayios Antonios (Nicos Papaevripides)

P7: VisMedNet, Malta ()

P8: De la Salle College sixth form, Malta (Maria Cachia)

Meeting Agenda

| Time | Issue | Partner |
| --- | --- | --- |
| 17:00 | Welcome and introduction | UNIC |
| 17.05 | Progress so far VisMedNet did not do the first activity, the O1/A4 and the methodological tool. If they do not do it until Monday 18/10, we will find somebody else to do it. Comparative report Deadline 30 November 2021 O1/A4 University of Macedonia VisMedNet Deadline 31/10/21 Activities Deadline for all activities 30 November 2021 Content of the project O1 O1/A1 National Teachers' and Children’s Needs Analysis O1/A2 National Analyses of the State of Art in the National Languages O1/A3 Group of Experts. O1/A4 Elaboration of the national reports in English O1/A5 Comparative Analysis O1/A6 The EURODIPLOMATS cultural diplomacy methodological tool O2 O2/A1 The EURODIPLOMATS Resources and Activities Toolkit - 1st version O2/A2 Workshops O2/A3 The EURODIPLOMATS Resources and Activities Toolkit - 2nd version O2/A4 EURODIPLOMATS Teachers' Handbook - O2/A5 EURODIPLOMATS Children's Handbook | UNIC All partners |
| 18.20 | Financial and administrative issues Send the contracts with the participating organisation of all people involved in the project Partner Agreement (Send the signed forms) | UNIC |
| 18.40 | Videos Each school has to prepare 4 videos Student to student (about the project) (2 min) Teacher to teacher (about the project) (2 min) Student to student about the methodological tool (2 min) Teacher to teacher about the methodological tool (2 min) Deadline 10/1/22 Dissemination Website –UNIC https://eurodiplomats.com/ Social media P2-Twiter account #EURODIPLOMATS (2 posts per month) P7-VisMedNet Create facebook account –post 4 posts per month P6-E-Twinning University of Macedonia –Slideshare De la Salle – Linked-in (2 posts per month) All partners should post on their organisation’s website a description of the project with a link to the website of the project. Next meeting (Spain) Friday 14/1/2022 Madrid Internal Evaluation Meeting evaluation | UNIC |
| 19:00 | End of meeting |  |